# Infrastructure Readiness & Verification Tracker

SFSU AT Canvas Remediation Program — Phase 1 (Document Remediation)

Aligned with the CSU ATI Digital Content Remediation Prioritization Framework (the Chancellor’s Office systemwide playbook). Tooling, licensing, and student-hiring funding below reflect that framework — confirm SFSU’s specifics with the campus ATI coordinator.

| Tracker owner | Last updated | Review cadence | Overall readiness (fill: __ of __ verified) |
| --- | --- | --- | --- |

Purpose

Track every piece of infrastructure the document remediation service needs, and verify each one actually works — not just “installed” but proven against its “Ready when” criterion. This is the operational readiness checklist; remediation procedures and open decisions live in separate documents.

How to use

Each row names a component and the “Ready when…” criterion that defines done. Fill in Owner, update Status, and record the Verified date + initials once the criterion is met.

Shaded gray cells are for you to type in.

“Verified” means someone confirmed it works against the criterion — e.g., actually ran a test file through the tool — not that it was merely purchased or installed.

Status legend:  ☐ Not started   ◐ In progress   ✓ Ready (unverified)   ✅ Verified   ⛔ Blocked (needs a decision)

# A. Tools & Software — Core Remediation

| Component / Ready when… | Owner | Status | Verified (date / initials) | Notes |
| --- | --- | --- | --- | --- |
| Adobe Acrobat Pro Ready when: licensed and installed on each student workstation, and a student has run Prepare for accessibility → Full Check on a test file. (CO ATI provides a 5-module student Acrobat training video series, ~70 min, in the ATI Remediation Hub; framework requires Acrobat proficiency even where Equidox is licensed.) |  | ❓ Confirm |  |  |
| Equidox (cloud PDF remediation) — CSU systemwide license Ready when: SFSU’s seats confirmed within the CSU systemwide Equidox license (72 concurrent users ≈ 3/campus; unlimited named accounts; more negotiable), FERPA/data-handling review completed, accounts provisioned, and a test PDF remediated + exported. |  | ◐ CSU-licensed – confirm seats + FERPA |  |  |
| Fullerton AI PDF remediation tool (CSU) — csu.d2ljzoawo09xv6.amplifyapp.com Ready when: access confirmed, capabilities and AI data-handling/FERPA reviewed, and a test PDF processed with output validated in PAC 2026. |  | ❓ Evaluate |  |  |
| ABBYY FineReader PDF (OCR) Ready when: access confirmed (via CSU ATI or purchase), installed, and a test scan has been OCR’d and exported to a tagged PDF. |  | ❓ Confirm |  |  |
| Allyant (CommonLook) — outsource / Tier-C lane Ready when: CSU Master Procurement Agreement finalized and pricing confirmed, and the Tier-C/overflow escalation routing to Allyant is defined (triggers: file too complex/large to be practical in-house, workflow at capacity, staffing shortage). |  | ◐ CSU MPA in progress |  |  |
| SensusAccess (optional, automated conversion) Ready when: evaluated as a self-service tool to auto-convert simple documents (offloading easy work); decide whether to adopt. |  | ☐ Optional |  |  |
| Microsoft Office (Word/PPT/Excel) Ready when: available to all students with the built-in Accessibility Checker present. |  | ✅ Assumed – confirm |  |  |
| Grackle (Google Docs/Slides) Ready when: available to remediate Google-authored content and export tagged PDFs (Google’s native PDF export is untagged); a test doc validated. Needed only if faculty author in Google. |  | ☐ Evaluate |  |  |
| Contrast checker (WebAIM / TPGi Colour Contrast Analyser) Ready when: a contrast-checking tool is available to students for color/contrast checks (WebAIM Contrast Checker is free/web; TPGi CCA is free/desktop). |  | ✓ Free – install |  |  |
| Screen reader — NVDA or JAWS Ready when: NVDA (free) or JAWS installed on a Windows machine and used to spot-check reading order — and, for STEM/math, a full NVDA listening check (see Section B; checker-clean ≠ readable for math). |  | ☐ Not started |  |  |
| PAC 2026 (PDF QA checker) Ready when: installed on a Windows machine and it validates a sample PDF, showing PDF/UA + WCAG results. (Framework prescribes PAC as the free PDF/UA validation gate.) |  | ☐ Not started |  |  |

# B. STEM / Math Remediation Tools

Suggested tools to evaluate for Tier-C STEM/math content (in the vein of EquatIO). ⚠️ The CSU STEM Course Materials Accessibility Working Group (NVDA testing, Dec 2025) found complex math garbled in EVERY pipeline tested — LaTeX→Pandoc HTML, MathML, R/Quarto HTML — even in files that pass tagging checks. So for math, “checker-clean ≠ readable”: the real QA gate is a human NVDA listening check. HTML beats PDF but is still imperfect; RStudio is unusable with screen readers. Coordinate with the systemwide STEM WG and outsource complex STEM (Allyant) rather than solving math alone.

| Component / Ready when… | Owner | Status | Verified (date / initials) | Notes |
| --- | --- | --- | --- | --- |
| MathType (Wiris) Ready when: available in the authoring workflow (Word/Google/LMS); can insert/edit accessible equations and export MathML; a test equation passes an NVDA listening check. |  | ❓ Evaluate |  |  |
| EquatIO (Texthelp) Ready when: licensed/available; can create accessible STEM content across Google and Microsoft and includes math OCR; a test passes an NVDA listening check. |  | ❓ Evaluate |  |  |
| Mathpix Snip (math OCR) Ready when: available to convert images/PDF math into LaTeX/MathML for remediation of math-in-images; a test conversion verified for accuracy. |  | ❓ Evaluate |  |  |
| Central Access Reader (free) / MathJax / LaTeXML (supporting) Ready when: a STEM reader (CAR) for QA, and web/source pipelines (MathJax renders MathML on Canvas pages; LaTeXML/Pandoc convert LaTeX source → accessible HTML+MathML) are identified for source-based math. |  | ☐ Note |  |  |
| Systemwide CSU STEM Working Group (escalation) Ready when: contact established with the CSU STEM Course Materials Accessibility WG as the escalation/coordination path for math accessibility, instead of solving it campus-alone. |  | ☐ Connect |  |  |

# C. Licenses & Access

| Component / Ready when… | Owner | Status | Verified (date / initials) | Notes |
| --- | --- | --- | --- | --- |
| CSU ATI licensed inventory Ready when: the SFSU ATI coordinator has confirmed in writing: SFSU’s Equidox seat count (in the 72-user pool), ATI Remediation Hub access, Allyant MPA status/pricing, UDOIT + TidyUP (CSU-negotiated), WebAIM Accessible Documents course, and CCC micro-courses. |  | ◐ Partly known |  |  |
| ATI Remediation Hub access (Canvas course) Ready when: the core team + students have access to the ATI Remediation Hub Canvas course — the framework doc, example job descriptions, the CO Acrobat student-training videos, and the Cal Poly MIDAS Commons template. |  | ☐ Request |  |  |
| UDOIT + TidyUP (CSU-negotiated) Ready when: UDOIT (scanning/alternate formats) and TidyUP (file cleanup) are available in Canvas for the TidyUP→UDOIT triage step. (Mainly Phase 2, but list the access here.) |  | ◐ Confirm |  |  |
| Canvas access for the team Ready when: each student has the Canvas role/access needed to reach the course content they will remediate (framework: Designer role; add students only to assigned courses, never to courses they are taking). |  | ◐ In progress |  |  |
| Box collaborative folder Ready when: the working group and students have appropriate access to the program content folder in Box. |  | ✅ Mostly done |  |  |

# D. Systems & Process

| Component / Ready when… | Owner | Status | Verified (date / initials) | Notes |
| --- | --- | --- | --- | --- |
| Remediation workstations (computers) Ready when: dedicated computers are set up with ALL required software loaded (Acrobat Pro, ABBYY, Equidox/Fullerton access, PAC 2026, NVDA/JAWS, MathType/EquatIO as needed, Office) and access to Canvas + Box; each student has a working station. |  | ☐ Not started |  |  |
| Intake channel + on-demand lane Ready when: the way work arrives is decided (mailbox / form / Box) and live, with a process note. Framework on-demand spec: file upload on the form, urgency + needed-by date, a cap on files per request, staff triage before assignment, and turnaround targets (24–48 hrs urgent; 2–3 business days standard); include staff/administrative docs. |  | ☐ Not started |  |  |
| Tracking log (minimal viable) Ready when: columns/schema defined and a live spreadsheet exists; every item logged at intake and closed with production metrics — including time-to-completion, so we build our own throughput averages (cf. Chico benchmarks). |  | ☐ Not started |  |  |
| Delivery & file-naming convention Ready when: the naming pattern and return location for finished files are documented in a process note. |  | ❓ Decide |  |  |
| Working-file storage Ready when: where originals, working copies, and deliverables live is defined — including FERPA-safe handling for any cloud tool. |  | ❓ Decide |  |  |

# E. People & Training

| Component / Ready when… | Owner | Status | Verified (date / initials) | Notes |
| --- | --- | --- | --- | --- |
| Student staffing (+ CO ATI hiring funds) Ready when: students are hired/assigned with hours and a named supervisor, using the CO ATI student-assistant hiring funds (FY24–25 IFT; round 2 allocated on demonstrated progress). Framework model: work-study first, over-hire + pre-train a bench, trickle-down training (train 3–4 core → student leads). |  | ◐ Team exists |  |  |
| Training access Ready when: the onboarding-path resources are reachable by students: CO Acrobat video series (Remediation Hub), WebAIM for Office, vendor materials for captioning — depends on the ATI licensing/Hub confirmation in Section C. |  | ◐ In progress |  |  |
| Certification path & practice sets Ready when: Tier A/B practice documents (with known issues) are built and the certification-gate rubric is set — implementing the framework’s “crosscheck certification” (early work peer/supervisor-reviewed before final). |  | ☐ Not started |  |  |

# F. QA & Verification

| Component / Ready when… | Owner | Status | Verified (date / initials) | Notes |
| --- | --- | --- | --- | --- |
| QA sign-off policy Ready when: the two-gate standard, the initial 100%-QA count per student, and the ongoing sampling rate are documented, and a QA reviewer is named. |  | ◐ Drafted |  |  |
| Checker stack in place Ready when: Acrobat Full Check + PAC 2026 available; the NVDA/JAWS spot-check process is documented; and — for STEM/math — a human NVDA listening check is the real gate (checker-clean ≠ readable). |  | ☐ Not started |  |  |

## Decisions this tracker depends on

Several rows are blocked on group decisions and CO-ATI confirmations (tracked separately in the decisions document): primary PDF tool (Equidox vs Acrobat vs the Fullerton/ASU AI tools) + FERPA reviews; SFSU’s Equidox seat count and the Allyant MPA status; SFSU’s IFT student-hiring funding (round-1 use / round-2 reporting expectations); STEM/Tier-C ownership and STEM-WG coordination; remediation-workstation provisioning; and intake & delivery conventions. Resolve those to unblock the ⛔ / ❓ rows.

## Related documents

CSU ATI framework (full reading): research/csu-ati-remediation-framework-reading.md

Per-type remediation SOPs: plans/phase-1/remediation-procedures/

File Format Remediation Tracker: Documents/File-Format-Remediation-Tracker.docx

Training catalog & onboarding: plans/phase-1/training/